## Auditor Instructions (hidden)
Template Instructions
For update meetings, utilize the "Audit Update" and the "Request Tracker". These documents will be shared with the agency and OFM.
For each update meeting, create a new "Audit Update" tab and name the tab the date of the meeting (i.e. 7.12.23). Leave the previous update meeting agendas in this file.
Once the new "Audit Update" agenda is completed for the upcoming meeting, export a copy of this tab and the "Request Tracker" into a new file outside of TeamMate to be shared with the agency and OFM.
**Do NOT delete completed requests from the "Request Tracker" - rows can be hidden or sorted for easier viewing.

## Request Tracker
DCYF/DSHS Audit Request Tracker |  | Do not delete requests once completed | [6 empty] | Pending Request(s):
0
Item # | Audit Area | Request Made To | Request Description | Date Requested | Original Due Date | Follow-Up Date (if past due) | Date Request Received | Notes Regarding Request Due Date | Status | # of Days Response Received Early/Late | If Past Due, Plan to get Requested Information?
1 | Planning/Fieldwork | Stefanie Niemela, DCYF | DCYF position description form or employment agreement | 2024-08-12 | 2024-08-21 |  | 2024-09-03 | followed up on 9/3, support provided shortly after | Past due/Completed | -13
2 | Planning/Fieldwork | Stefanie Niemela, DCYF | Normal documented work schedule from DCYF. Last contact about this was that "Ann is researching this, particularly the Thursday and Friday shifts that appear to overlap with his scheduled hours at DSHS.". We are aware that the position at DCYF is on call and he is onsight when called in, hes an hourly employee, and fills outa timesheet and is overtime exempt. | 2024-08-12 | 2024-08-21 |  | 2024-09-03 | followed up on 9/3, support provided shortly after | Past due/Completed | -13
3 | Fieldwork | Stefanie Niemela, DCYF | Monthly outlook calendar from DCYF dating back to December 2018 | 2024-08-12 | 2024-08-21 |  | 2024-09-03 | Per DCYF: "HR doesn’t have access to his Outlook calendar, they would have to ask his supervisor and when they last spoke with the SAO they didn’t want HR to alert his supervisor or manager. Stefanie will contact IT, but HR doesn’t believe many of our on-call employees utilizing their Outlook calendar." | Past due/Completed | -13
4 | Fieldwork | Rick Meyer, DSHS | Monthly outlook calendar from DSHS dating back to December 2018 | 2024-08-12 | 2024-08-21 |  | 2024-09-05 | received binders from Rick | Past due/Completed | -15
5 | Fieldwork | Stefanie Niemela, DCYF | DCYF Timesheets for the subject dating back to December 2018 | 2024-08-12 | 2024-08-21 |  | 2024-09-03 | followed up on 9/3, support provided shortly after | Past due/Completed | -13
6 | Fieldwork | Rick Meyer, DSHS | DSHS Leave slips/record dating back to December 2018 | 2024-08-12 | 2024-08-21 |  | 2024-08-20 |  | Completed on time | 1
7 | Fieldwork | Stefanie Niemela, DCYF | Any outside employement agreement or equivelent showing the employee agreed to disclose any outside employment or conflicts of interest, or employment at another government agency. | 2024-08-12 | 2024-08-21 |  | 2024-09-03 | followed up on 9/3, support provided shortly after | Past due/Completed | -13
8 | Fieldwork | Stefanie Niemela, DCYF | Any DCYF policies regarding core work hours or hours employees are authorized to work (e.g. 10am - 3PM core work hours and employees unable to work prior to 6am or after 6pm), if in existence. | 2024-08-12 | 2024-08-21 |  | 2024-09-03 | followed up on 9/3, support provided shortly after | Past due/Completed | -13
9 | Fieldwork | Rick Meyer, DSHS | Any outside employement agreement or equivelent showing the employee agreed to disclose any outside employment or conflicts of interest, or employment at another government agency. | 2024-08-12 | 2024-08-21 |  | 2024-08-20 |  | Completed on time | 1
10 | Fieldwork | Rick Meyer, DSHS | Any DSHS policies regarding core work hours or hours employees are authorized to work (e.g. 10am - 3PM core work hours and employees unable to work prior to 6am or after 6pm), if in existence. | 2024-08-12 | 2024-08-21 |  | 2024-08-20 |  | Completed on time | 1
11 | Fieldwork | Rick Meyer, DSHS | DSHS position description form or employment agreement | 2024-09-11 | 2024-09-18 |  | 2024-09-12 |  | Completed on time | 6
12 | Fieldwork | Stefanie Niemela, DCYF | Question regarding notification of outside employment form sent via email. | 2024-09-11 | 2024-09-18 |  | 2024-09-12 |  | Completed on time | 6
13 | Fieldwork | Stefanie Niemela, DCYF | Copy of CHI Franciscan health outside employment form and report showing faliure to make required annual attestations regarding outside employment | 2024-09-12 | 2024-09-19 | 2024-10-03 | 2024-10-09 |  | New due date/Past due/Completed | -6
14 | Fieldwork | Stefanie Niemela, DCYF | Request to provide DCYF Timesheets in excel format | 2024-09-16 | 2024-09-25 |  | 2024-09-25 |  | Completed on time | 0 | DCYF couldn't find a way to run an excel export of these records. Resorted to using the PDF version.
15 | Fieldwork | Rick Meyer, DSHS | Request for further time entry data for the subject dating back to January 2018. as well as question regarding time entries. See email sent on 9/25 | 2024-09-25 | 2024-10-04 |  | 2024-09-27 |  | Completed on time | 7 | See email explanation reply at B.1.29
16 | Fieldwork | Stefanie Niemela, DCYF | Request for information regarding timecodes. See email sent on 9/25 | 2024-09-25 | 2024-10-04 |  | 2024-09-25 |  | Completed on time | 9
17 | Fieldwork | Stefanie Niemela, DCYF | Request for further information regarding Daniel Kresse start date at DCYF and employment history timeline. See email sent on 9/30 | 2024-09-30 | 2024-10-07 |  | 2024-09-30 |  | Completed on time | 7
18 | Fieldwork | Stefanie Niemela, DCYF | History of HRMS pay rate changes for Daniel Kresse dating back to January 2018. See email sent on 9/30/2024 | 2024-09-30 | 2024-10-07 |  | 2024-09-30 |  | Completed on time | 7
19 | Fieldwork | Rick Meyer, DSHS | History of HRMS pay rate changes for Daniel Kresse dating back to January 2018. See email sent on 9/30/2024 | 2024-09-30 | 2024-10-07 |  | 2024-10-08 |  | Past due/Completed | -1
20 | Fieldwork | Stefanie Niemela, DCYF | Question regarding missing DCYF February timesheets. Email sent on 10/3 | 2024-10-03 | 2024-10-10 |  | 2024-10-10 |  | Completed on time | 0
21 | Fieldwork | Stefanie Niemela, DCYF | Request for date of change from social service specialist to social service Supervisor and position description form for a social service supervisor | 2024-10-11 | 2024-10-18 |  | 2024-10-19 |  | Past due/Completed | -1
22 | Fieldwork | Stefanie Niemela, DCYF | Request for supervisor interview (DCYF) | 2025-01-07 | 2025-01-16 |  | 2025-01-28 |  | Past due/Completed | -12
23 | Fieldwork | Rick Meyer, DSHS | Request for supervisor interview (DSHS) | 2025-01-07 | 2025-01-16 |  | 2025-01-30 |  | #REF! | -14
24 | [9 empty] | 0
25 | [9 empty] | 0
26 | [9 empty] | 0
27 | [9 empty] | 0
28 | [9 empty] | 0
29 | [9 empty] | 0
30 | [9 empty] | 0
31 | [9 empty] | 0
32 | [9 empty] | 0
33 | [9 empty] | 0
34 | [9 empty] | 0
35 | [9 empty] | 0
36 | [9 empty] | 0
37 | [9 empty] | 0
38 | [9 empty] | 0
39 | [9 empty] | 0
40 | [9 empty] | 0
41 | [9 empty] | 0
42 | [9 empty] | 0
43 | [9 empty] | 0
44 | [9 empty] | 0
45 | [9 empty] | 0
46 | [9 empty] | 0
47 | [9 empty] | 0
48 | [9 empty] | 0
49 | [9 empty] | 0
50 | [9 empty] | 0
Note on B3: Metzler, Cassandra (SAO): Keep naming convention consistent to allow proper sorting